## Sheet1
A. Electric Car Club Organization
a.Discuss the Club Charter, Elect Officers and Project Leaders.
b. Set Goals and Timetable.
c.General Discussion of Project Tasks
B. Initial Design Specification
a.Assign 3 teams to produce 3 separate sets of design specifications for subsequent evaluation
b. Review Designs for Compliance with Electrathon Requirements
c.Select a Design for Construction
C. Construction Drawings
a. AutoCad Drawings from Selected Design Specification
b. Review designs for compliance with Electrathon Specifications
c. Use the Stability Spreadsheet from Documents
D. Construction Drawing Reviews
a. Review designs for compliance with Electrathon Specifications
b. Use the Stability Spreadsheet from Documents link to check stability
E. Make Cost Estimates of Materials and Racing Costs
a. Make Cost Estimates from Drawings
a. Get Component Pricing and Build a spreadsheet of Vendors Info Sheet with Links to Part Numbers, and Pricing Sheet.
b.Racing Costs equipment Requirements
i.helmets, trailer and lodging
c. Shop Tool Purchases and outside services (welder)
F. Procurement and Sponsorships
a.Set appointments present Drawings and estimates for Sponsorships
b. Document material and Funding commitments. Letters of Thanks and Arrangements for transfers and deliveries
G. Construction and Assembly
a.Find a suitable secure area to build the Electrathon and for Materials Storage. Establish Inventory Methods
b. procure the necessary machine tools and talent.
c. Review Safe Equipment Usage and Personal Safety Equipment Requirements.
d.Cut Assemblies
e. Order of Assembly and Structural Fabrication.
H. Startup and Bench Testing Procedures
a. Mechanical and Electrical Testing: Brakes operate correctly, Are the electrical hookups correct i.e. fusing in place, no evident shorts.
b.Initial Controller configuration. Rpm measurements and initial gear ratio determination.
I. Race Training and Logistics
a.Safety Plan.Establish safety procedures for the Drivers and Pit Crew:
i.Inspect car and test track for Readiness.
ii. Test Track Access Procedures Control:
who and where personnel can be on the track.
b. Written Testing Plan
i. Slow and Easy Car performance checks:Rattles, Stability assessment,wheel scuffing,excess amp draw.
c.Train Drivers and Mechanics Training Race
i. Driver Proper Attire no loose long hair jewelry or baggy clothing
ii. Pit Crew Troubleshooting and on the fly repairs:Flats, axles, blown fuses
d. Data Collection: amp draw, lap times and voltage
f. Race Travel Preparation Procedures